## RMMM Plan
Election Voting System
Introduction About the Project
The purpose of this section is to provide the reader with a general, background information and an insight into the mobile application of “Election Voting System” and is to specify the requirements for policy enforcement framework for E-Voting
Risk Sheet
| Risks | Category | Probability | Impact | Cost of Failure | Risk Exposure
1 | Overdue Dates | SR | 45% | 3 | 100 | 45
2 | Lack of Budget | BGR | 70% | 2 | 400 | 280
3 | Aligning Stakeholders | OP | 35% | 3 | 120 | 42
4 | Compatibility issues with NADRA API | TAR | 50% | 1 | 150 | 75
5 | Problems with Voter Authentication | TER | 40% | 2 | 1200 | 480
6 | Voter counting | OP | 35% | 2 | 500 | 175
7 | Staff on leave | IR | 30% | 3 | 1000 | 300
8 | Inadequate testing | QR | 40% | 2 | 200 | 80
9 | Insufficient preparing | OP | 20% | 4 | 400 | 80
10 | Performance Support | PR | 25% | 4 | 1500 | 375
11 | User Training | QR | 25% | 4 | 250 | 62.5
12 | Internet Issues | OPR | 25% | 3 | 300 | 75
13 | Business needs customization | BR | 15% | 2 | 500 | 75
Impact Values: 1 – Catastrophic 2 – Critical 3 – Marginal 4 – Negligible
RISK NAME |  | MITIGATION | Monitoring | Management
1 | Lack of Budget | we will ask budget from customer | Software development budgets can change as project scopes change, but it's important to monitor projects so that they don't go over budget | We will adjust project plan and budget whenever changes are made to reduce raising project costs.
2 | Aligning Stakeholders | We will set meeting every week. Any confusion from any stakeholders will be answered. | We will regularly assess the effectiveness of the communication strategies and channels. We will monitor for signs of communication breakdowns, such as unanswered emails, misunderstandings, or stakeholder disengagement. | We will schedule meeting and ask feasible time from all stakeholders.
3 | Overdue Dates | We will set responsibilities and roles, and will see what are my team capabilities. | You have a set deadline in place, but one thing after another puts you behind schedule. This results in stakeholder frustration and unforeseen expenses. | We will see the progress of all the team and track them.
4 | Compatibility Issues with NADRA API | We will check the version and test its api whether API is working well or not. Then we will integrate it with software. Because NADRA API can be updated | we will regularly check for API updates and will ensure that the software remains compatible with new versions. | Conduct rigorous testing to verify the compatibility of the software/system with the NADRA API.
5 | Insufficient preparing | Develop a detailed project plan that outlines objectives, tasks, timelines, resources, and dependencies. Identify any skill gaps within the team and provide training or professional development opportunities to bridge those gaps. | Any successful innovation implementation requires putting in the time and effort necessary to provide proper preparation and support throughout execution. Because of the stage's underuse, several initiatives are said to have failed.. | Your learning and advancement team will be fully utilising the technology and creating the most engaging learning experiences if they are well prepared in every area of the stage.
6 | Inadequate testing | We will check all kinds of vulnerabilities and bogus voting possibilities | This is especially valid for E-Voting as we need to have a bogus-free voting. | Ensure that all kinds of security testing is done.
7 | Performance Support | We will check that each module is performant. | We will monitor the time taking to respond individual user as well as for multiple users. | We will check each API is working well, and can integrate with software easily without any defect.
8 | User Training | Individual user should have their own transactional Flows which they will perform on the system. | Transactional flow document should be in a softcopy or in hard copy. | Transactional Flow documents should be according to the work flow of the user.
9 | Internet Issues | we should have another internet service as a backup. Or must have mobile data package | we should ensure that a backup internet is working well. | we should build the software in such a way that it won't stop working when the internet is down, instead when the internet starts working all the vote counting should sync with the database automatically.
10 | Business need customization | we should make our software flexible. | we should be ready for all the changes we have to make if we have to change something in the software. | we should make our software in such a way that it can handle the changes made in it and if the changes failed then it could be easily restore to its original version.
11 | Problems with Voter Authentication | Implement strong encryption and authentication protocols. Use multi-factor authentication. | Regularly monitor access logs and audit trails for any unauthorized access attempts. | Have a response plan in place for immediate action if unauthorized access is detected.
12 | Voter Counting | We will check real-time update for vote counting | We will use automation tools like appium for load testing | We should check any mismatch between counting stored in database and UI
13 | Staff on leave | Identify backup personnel or resources who can step in during the absence of key staff members. | Continuously monitor the schedule of staff leaves to identify potential overlaps or extended absences that might impact the project. | Implement a leave planning system that ensures staff members schedule their leave in a way that minimizes its impact on project timelines.